|  |  |  |
| --- | --- | --- |
| **Tasks** | **Duration (Days)** | **Predecedors** |
| A | 3 | - |
| B | 4 | A |
| C | 2 | A |
| D | 5 | B |
| E | 1 | C |
| F | 2 | C |
| G | 4 | D, E |
| H | 3 | F, G |

* **Basic Scheduling**

**When is the delivery date?**

* The delivery will be after 19 days

**Which task could be delayed without delaying the schedule?**

* E (Can be delayed for 6 days)
* F (Can be delayed for 10 days)